## SFP
Recruitment Activity | Dates | Role
SFP vacancy created | 2022-08-01 | UKFPO
SFP upload to Oriel | 19th August 2022 | YHFS
Upload Nomination data to Oriel | 19th August 2022 | YHFS
Registration window (on Oriel application system) for applicants | 25 August (09:00 BST) – 07 September 2022 | Applicants
**The Oriel application system will be offline for planned downtime on 31 August (and potentially also on 1st September). ** 31 August – 01 September 2022
National application window for FP, FPP, SFP programmes | 07 (09:00 BST) – 20 September 2022 (12:00 midday BST) | Applicants
Foundation Schools/SUoAs hold Specialised Foundation Programme selection processes | 21 September– 30 December 2022 | YHFS
Send applicants Self-Assessment / White Space Questions | 21st September | YHFS
Deadline for return of Self-Assessment / White Space Questions | 2nd November | Applicants
Review Self-Assessment / White Space Questions | 2nd November-10th December | YHFS
Upload Self-Assessment / White Space Questions scores to Oriel | 11th December | YHFS
Run Programme Match (not to be released until national deadline) | 11th December | YHFS
Specialised Foundation Programme offers released – Round 1 | 2023-01-11 | UKFPO
Specialised Foundation Programme offers released – Round 2 | 18 – 20 January 2023 | UKFPO
Specialised Foundation Programme offers released – Round 3 | 25 – 27 January 2023 | UKFPO
Specialised Foundation Programme offers released – Round 4 | 01 – 03 February 2023 | UKFPO
Evidence to be sent by successful applicants to be validated | 11th Jan - 5th February 2023 | Applicants / YHFS
Specialised Foundation Programme clearing round | 06 – 10 February 2023 | UKFPO
Please note that all times published are UK local time. The UKFPO will endeavour to release outcomes/communicate with applicants as early as feasible on each stated date
Please note the above timeline doesn not include eligibility, SJT or clinical asssessment information. Please see the UKFPO website for the complete timeline