## Slide 1: Quality Improvement Project
Dr Chris Webb - December 2020
QIP

## Slide 2
The trainee is in good position to identify areas of practice that frustrate them and that possibly have an impact on patient safety. During their primary care posts in ST1 /2 they are required to complete a quality improvement project with the aim of improving patient care. Audit is a type of QIP as both look at the quality of care provided with the aim of improving it and both require measurements to demonstrate change. More generally, QIPs can be about making small incremental changes and measurements which may be done weekly to test the impact of the changes. In contrast an audit has set criteria, each with their own defined standards, and has two sets of measurements over a longer time period, to demonstrate a baseline and then improvement. Completing a QIP allows change to be tested both quickly and successfully and is easier to do in a short time frame, for example in a 4-6 month trainee post. The QIP should be written up in the relevant section on the Portfolio and the supervisor will both assess and discuss this with them

## Slide 3: RCGP Curriculum 2018
Maintaining Performance Learning and teaching
Critically reviewing experience in practice should become a habit that is maintained over the whole of your professional career. Knowing and applying the principles of lifelong learning and quality improvement should be considered an essential competence for every GP
Participate in personal and team performance monitoring activities and use these tools to evaluate practice and suggest improvements

## Slide 4: GMC Generic Capabilities 2016
All trainees should design and implement quality improvement projects that improve clinical effectiveness, patient safety and patient experience by:
Using data to identify areas for improvement
Examining information from audit, inquiries, critical incidents or complaints, and implementing appropriate changes
Employing quality improvement methods, such as plan, do, study, act cycles
Undertaking the importance of patient and public involvement in decision making at group level and when changes to services are proposed
Engaging with stakeholders, including patients, doctors and managers, to plan and implement change
Effectively measuring and evaluating the impact of quality improvement interventions)

## Slide 5: Why QIP?
Trainees should “Take part in regular and systematic clinical audit and/or quality improvement” - Gold Guide 2017
“A progressive curriculum in quality improvement activity should underpin all training stages of a doctor, building capability and leadership, and a foundation for on-going lifelong learning and implementation” - Academy of Royal Colleges, March 2016

## Slide 6: Undertaking a QIP
It needs to be decide what the aim of the project is going to be
Projects can be chosen following a significant event, a patient complaint; or an area of care they feel passionate about
Do not make the project too complicated; it needs to be completed within a primary care placement in ST1/2
The project should aim to improve patient safety or care and be ‘SMART’

## Slide 7: SMART
Specific - do not make it too broad and chose something of interest. Words such as increase / reduce help to set a clear goal
Measurable - ensure that there is something they can easily measure to demonstrate any change. It can be qualitative data (descriptive) as well as quantitative data (numerical data)
Achievable - ensure the data is easily collectable and keep the aims simple
Relevant - project should be focused on patient safety
Time defined - choose something that can be done in the time frame. They need to be able to complete their project in their primary care placement

## Slide 8: Audit
Identify a problem
Define standards
Collect data
Analyse
Implement change
Re-audit

## Slide 9: Model for Improvement
Aim - What are we trying to accomplish?
Measure - How will we know if a change is an improvement?
Change - What changes can we make that will result in improvement?
PSDA cycle
  Plan - Objective questions and predictions (why). Plan to carry out the cycle (who, what, where, when)
  Act - What changes are to be made? Next cycle?
  Study - Complete the analysis of the data. Compare data to predictions. Summarise what was learned
  Do - Carry out the plan. Document problems and unexpected observations. Begin analysis of the data
Asks three questions:

## Slide 10: Repeated PDSA cycles work towards the AIM
What am I trying to achieve?
How will I know a change is an improvement?
What changes can I make that will result in the improvement

## Slide 11: WBPA QIP
Expect to do in ST1-ST2, ideally during GP placement
Marked against agreed standards in a similar way to COTS and mini-CEX’s
No pass or fail but will contribute to evidence in the related competencies: (Fitness to practice; maintaining performance learning and teaching; data gathering and interpretation ; working with colleagues and in teams; organisation management and leadership)
Trainees write up project and share with ES. No further changes made. ES provides feedback (may be aware of impact in practice)

## Slide 12: Unsatisfactory project
No team engagement
No engagement of stakeholders (people affected by change including patients)
No or minimal measurement
No real attempt at implementing change, just a discussion that change should happen

## Slide 13: QIP Template & Feedback Level Descriptors

## Slide 14: The GP Trainee Assessment Framework
Project Title and why it was chosen
Project Aim
Describe what baseline data or information you gathered
Describe what subsequent data or information you gathered
How did you plan and test out your changes?
How have you engaged the team, patients and other stakeholders throughout the project?
Summarise the changes as a result of your work and how these will be maintained
What have you learnt and have you got any outstanding learning needs?
Overall competence at which the trainee has shown that they are performing is assessed at the end

## Slide 15: 1. Project Title and why it was chosen
You should explain what trigger (case, data or events) led you to look at this area
You should comment on the likely impact of this on patients, and review the guidance or evidence that is relevant to the area (e.g. a literature review)

## Slide 16
Below expectations
  Title is unclear or confusing, or has no significant justification based on links to personal or practice needs
  There is no reflection on the known guidance or evidence relating to this area. There is no consideration of the impact on patients
Meets expectations
  Clear title which is understandable, and has a link to personal or practice needs
  There is reference to some appropriate guidance and/or to evidence
  There is consideration of the impact of the QIA on patients
Above expectations
  The title and reasons are clear and are based on an identified practice need or clear personal experience
  The guidance and evidence that is identified is appropriate, clear and well chosen (not excessive)
  The assessment of impact on patients includes reference to prevalence/ incidence and severity etc
  Assessment of impact considers how teamwork has been made more effective
Project Title and why it was chosen

## Slide 17: 2. Project aim
When explaining your project aim, consider what you are trying to accomplish, how will you know that a change is an improvement and what change you could make that would result in an improvement in patient safety or patient care?

## Slide 18
Below expectations
  The aim is vague with no specific goal or time frame.
  There is no clear consideration of what is being accomplished or that a suggested change is an improvement.
  It is not clear how the project will improve patient safety or patient care
Meets expectations
  The goal set is specific with a clear time frame
  There is consideration of what is being accomplished or that a suggested change is an improvement
  There is some suggestion that there is a connection with patient safety and/or patient care
Above expectations
  The aim is summarised in a SMART (Specific, Measurable, Achievable, Relevant and Time defined) format
  There is clear consideration of what is being accomplished and that a suggested change is an improvement
  It is clear how the project will improve patient safety or patient care
Project aim

## Slide 19: 3. Describe what baseline data or information you gathered
You should explain how you understood the current position in order to decide that improvements were needed. Explain which QI tools or methods you used to fully understand the ‘problem’ you were trying to solve. Suitable methods would include QI tools for example; assessing baseline data, process-mapping, conducting a survey and using fishbone analysis.
Quality improvement requires attempting to measure some change, though the nature of the measurement will be different in different projects and some data could be available before the start of your personal involvement.

## Slide 20
Below expectations
  Insufficient information is provided to demonstrate the ‘problem’ was fully understood prior to the improvement being designed and implemented
  It is unclear which QIA process/processes or tools have been used or those used have not been followed through appropriately
Meets expectations
  There is enough evidence obtained to demonstrate the ‘problem’ was fully understood prior to implementing improvements
  There is a clear and appropriate use of a recognised QIA process/ processes or tools
Above expectations
  The evidence which is obtained is well chosen and may be of different types using a range of QI tools. There is justification of the amount of evidence obtained (i.e. explanation of why there is not more or less evidence)
  There is clear presentation of the evidence
  The selection and use of tools for improvement has been well justified for the project
Describe what baseline data or information you gathered

## Slide 21: 4. Describe what subsequent data or information you gathered
How did you measure and evaluate the impact of change?
Please share enough data to demonstrate outcomes; you may not need to share all your data

## Slide 22
Below expectations
  The data shared is not capable of demonstrating the changes suggested e.g. because of the way it has been collected, or because the data is not appropriate
Meets expectations
  The data provided is clear and the evaluation of the data is appropriate and considers other possible causes for the changes observed.
  Data collection is relevant and is collected over time though could have been more comprehensive.
Above expectations
  The data is well presented; clearly evaluated and well chosen
  There is evidence of multiple data collection at appropriate intervals in time
  There is an understanding of the potential limitations of different methods of data collection
Describe what subsequent data or information you gathered

## Slide 23: 5. How did you plan and test out your changes?
Effective QI work involves testing out changes (small cycles of change) and then learning from this experience and building on it
How did you apply this principle to your QI project?

## Slide 24
Below expectations
  There is no evidence of small cycles of change or use of model for improvement or PDSA (Plan, Do Study Act)
Meets expectations
  There is a clear and appropriate use of a PDSA cycles in the planning and implementation of the project
Above expectations
  The project shows clear evidence of a PDSA approach
  There is evidence of multiple and sequential tests of change
How did you plan and test out your changes?

## Slide 25: 6. How have you engaged the team, patients and other stakeholders throughout the project?
Describe any challenges of getting different team members engaged with your QIA
Describe how you maintained momentum e.g. planning for an early win:win

## Slide 26
Below expectations
  There is no team input or the description of this is unclear
  There is inadequate reflection on steps taken to engage stakeholders
  There is inadequate reflection on the challenges of engaging different team members with no reflection on personal learning from this
Meets expectations
  There is a description of how different stakeholders were engaged which includes patient involvement
  There is description of the challenges of engaging particular stakeholders which remains focused on this event
Above expectations
  The description of how stakeholders (including patients) were engaged demonstrates insight into the need for adaptability and generating win : win positions
  There is reflection on the particular difficulties of engaging some individuals or patient groups and thoughts on personal learning from this for the future
  The different roles of team members in the team are considered and used productively
How have you engaged the team, patients and other stakeholders throughout the project?

## Slide 27: 7. Summarise the changes as a result of your work and how these will be maintained
If improvement was not achieved, explain why and what you learnt about this
Describe how you relayed your results to the team and the feedback you received

## Slide 28
Below expectations
  The summary provided is not clear or specific, or the conclusions offered are n9t consistent with the earlier work. There is a reliance of people following new protocols and human behavioural change in order for the changes to be sustained. There is no clarity about the sustainability of the changes
Meets expectations
  The summary of the changes is clear and appropriate. There is a clear consideration of steps to enable maintenance of changes. There is evidence of an understanding of the role in changing systems to embed improvement. Change has been embedded by the organisation
Above expectations
  The summary of changes is clear and broken down to demonstrate how each part can be maintained. There is evidence that systems have been changed so that it is harder to revert to old processes and easier to continue to follow the new processes. This will ensure that change is embedded and sustainable ie not just a protocol
Summarise the changes as a result of your work and how these will be maintained

## Slide 29: 8. What have you learnt and have you got any outstanding learning needs?
Think about what you will maintain, improve and stop in QIA?
It is important to consider what changes you might need to make as you continue to engage with QIA, for example consider the size of project, the amount of evidence collected, how you worked with others, the effective use of IT, its value to long term care and its impact on sustainability (health outcomes for patients and populations from an environmental, social and financial perspective)

## Slide 30
Below expectations
  There is little reflection on the personal learning from the QIP which has been completed and how to use this is future QIP, leadership, or other situations
Meets expectations
  The reflection on QIP demonstrates appropriate personal learning about leading change and choosing effective tools to enable improvements to patient care / safety / experience. Consideration has been given to the value and sustainability of the QIP
Above expectations
  The reflection on this QIP goes beyond the meets expectations descriptors and is clearly linked to plans for future QIP in a realistic and clear way. The QIP highlighted the impact of sustainability on health outcomes from several different perspectives
What have you learnt and have you got any outstanding learning needs?